## Group Contribution Log
Course | CS3343
Term | 2022-23 Semester A
Project No. | 28
Project Name/Title | River Crossing Game (with customizable puzzle and solver)
No. of Team Members | 5
Project Manager Name | Chin Man Chong
Student ID | Name (Last, First) | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Total | Student | Relative | Contribution | Group Mark | Final Adjusted
| Chin Man Chong | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 130 | Chin Man Chong | 1 | 100% |  | 0
| Chau Wai Tong | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 130 | Chau Wai Tong | 1 | 100% |  | 0
| Chau Tsun Yu | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 130 | Chau Tsun Yu | 1 | 100% |  | 0
| Fung King Shun | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 130 | Fung King Shun | 1 | 100% |  | 0
56618753 | Lam Kin Hei | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 130 | Lam Kin Hei | 1 | 100% |  | 0
[15 empty] | 0 | 0 | 0 | 0% |  | 0
| Total Effort | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 650 | Max | 1 |  | Average | 0
[19 empty] | Max | 0
[19 empty] | Min | 0

## Weekly Activity Log
Time period by week number |  | Weekly Activity Log of Group 28 | Routine Meeting Attendees | Logged By
Week 1 (week 35, 2022) | Objectives: | Brainstorm project ideas, and discuss project direction. | All members | Jerry
| Completed Tasks: | Discussed software architecture (incl: front-end & back-end), brainstormed project titles (incl: web application, mobile app, console games)
| Next Tasks: | Each member present at least one project idea suggestion and the initial feasibility studies. Vote for one of the ideas for starting the project.
Week 2 (week 36, 2022) | Objectives: | Each member presents their finding and investigates different project idea and their pros and cons. | All members | Jerry
| Completed Tasks: | Project idea suggestions: Cross River Game/by Jerry; Battle Ship Game/by Julian; Mastermind/by Sam; Game Solver/by Peter Voting result: Project title -> Cross River Game with Solver. Discussed Project Jobs distributions. Created a GitHub repository.
| Next Tasks: | Futher study about the game flow/by Jerry & Brian, logic/by Julian, UI/by Sam, solver/by Peter, & basic test cases+report/by Brian.
Week 3 (week 37, 2022) | Objectives: | Create an initial plan, and discuss the scope of the project. And start to develop use case specifications. | All members | Jerry
| Completed Tasks: | Rename project title -> River Crossing Puzzle with Solver Project scope decided: Full console UI (maybe with colour text), Custom game mode, Default game mode (with easy, normal, and hard levels), Solver mode (algorithm without AI)
| Next Tasks: | Further studies of Report template/by Jerry, Coding: UI/by Sam, Logic/by Julian, Solver/by Peter, Test report & test cases/by Brian.
Week 4 (week 38, 2022) | Objectives: | Enter the coding stage (phase 1). Discuss program implementation details, game flow and logic. Create the first version of the class diagram. | All members | Jerry
| Completed Tasks: | Decided High-level game flow. Appointed JSON struct file as game logic (for open-close principle purposes) Discussed and decided on Project Development Methodology -> Overall in Concurrent Engineering Model + Each module in Spiral Model
| Next Tasks: | Study bug report format & test cases/by Brian. Continue writing the project plan by Jerry Forecast phase 1 completion date by rounding up coding progress/by Sam, Peter & Julian
Week 5 (week 39, 2022) | Objectives: | Develop a river crossing game prototype. Write about the constraints and develop tools for the report. Coding progress (deadline of each phase) discussions. | All members | Jerry
| Completed Tasks: | Decided mid-Oct as the coding deadline for version 1.0 Pre-Release v0.1.0 merged on GitHub Initial game flow decided in 3 levels-> easy, normal, hard + custom rule
| Tasks in Progress: | Coding of UI/by Sam; Logic/by Julian; Solver/by Peter; Test cases study/by Brian. Project reports drafted/by Jerry. Bug report template & draft/by Brain.
| Next Tasks: | Test cases coding preparation/by Brain. Include more detail in the analysis and design report UI colour text study/by Sam. Improve logic engine from O(n^2) to O(n)/by Julian.
Week 6 (week 40, 2022) | Objectives: | Record the game prototype release and its feature, and continue to develop different functions and game modes. Start writing test cases. | All members | Jerry
| Completed Tasks: | Logic engine prototype in O(n) completed. Test cases sudo-code completed.
| Tasks in Progress: | Coding of UI/by Sam; Logic/by Julian; Solver/by Peter; Test cases study/by Brian. Coding test cases/by Brain. Project reports drafted/by Jerry. Bug report template & draft/by Brain. UI colour text study/by Sam.
| Next Tasks: | Test cases trials on UI + logic module/by Brain.
Week 7 (week 41, 2022) | Objectives: | Develop solver logic. And continue program testing for the gaming part. Write a more detail project plan. | All members | Jerry
| Completed Tasks: | Pre-Release v0.9.5 merged on GitHub. Bug report template/formate decided.
| Tasks in Progress: | Coding of UI/by Sam; Logic/by Julian; Solver/by Peter; Test cases study/by Brian. Coding test cases/by Brain. Project reports drafted/by Jerry. UI colour text study/by Sam. Test cases trials on UI + logic module/by Brain.
| Next Tasks: | Write project development methodology section on the report/by Julian
Week 8 (week 42, 2022) | Objectives: | Fix some bugs accounting for the testing results. Record the change in the report, writing more about the design detail. | All members | Jerry
| Completed Tasks: | The project development methodology section finished writing. UI colour text display works smoothly under Windows & Linux OSs. The first game prototype was completed. Pre-Release v1.0.0 merged on GitHub.
| Tasks in Progress: | Coding test cases/by Brain. Project reports drafted/by Jerry, and Julian. Test cases trials on UI + logic module/by Brain.
| Next Tasks: | Finetune coding and rewrite to apply coding patterns. UI module/by Sam, Logic module/by Julian. High-level use-case descriptions & diagrams, sequence diagram/by Jerry Module level classes diagram & sequence diagrams/by Sam, Peter & Julian. Bug reports writing/by Brain. Export project jar, then test run on different OSs (Windows 10, Linux, IOS)/by Julian
Week 9 (week 43, 2022) | Objectives: | Release the solver version, and write the usage method on the report. Start testing the solver. Re-discuss game flow to decide on easy, normal & hard game modes. | All members | Jerry
| Completed Tasks: | jar file test runs on different OSs (Windows 10, Linux, IOS) finished.
| Tasks in Progress: | Finetune coding and rewrite to apply coding patterns. UI module/by Sam, Logic module/by Julian. Finetune test cases/by Brain. Project reports drafted/by Jerry, Brian, Peter, and Julian. Bug reports writing/by Brain.
| Next Tasks: | Write Normal game rule/by Julian
Week 10 (week 44, 2022) | Objectives: | Finalize written all the testing results in testing and bug reports. And wrote the user guide and installation environment. Discuss code refactoring. | All members | Jerry
| Completed Tasks: | Code rewriting completed -> Singletone, Command pattern & Factory pattern in UI module; Factory pattern in the Logic module. High-level use-case descriptions & diagrams, sequence diagram completed. Module level classes diagram & sequence diagrams completed. 11 Bug reports finished using Bugzilla. Family.json rule for normal game mode finished.
| Tasks in Progress: | Finetune test cases/by Brain. Project reports drafted/by Jerry, Brian, Peter, and Julian.
| Next Tasks: | Write detail descriptions of all diagrams/by Sam, Peter, Jerry & Julian Rewrite ActivityLog with tasks details and responses members/by Jerry Discuss project ppt & code refactoring.
Week 11 (week 45, 2022) | Objectives: | Re-discuss code refactoring details to improve code quality and time complexity. Re-discuss ppt for the presentation meeting. | All members | Jerry
| Completed Tasks: | Rewrite ActivityLog completed. Details descriptions of diagrams added to the project.
| Tasks in Progress: | Adding more detail and explanation in the report/ by Jerry. Conduct more testing/ by Brian.
| Next Tasks: | Continue review and modify code by Julian, Peter and Sam.
Week 12 (week 46, 2022) | Objectives: | Finalize all code, project plan, analysis and design, testing and bug reports. | All members | Jerry
| Completed Tasks: | Jobs allocation for the presentation slides.
| Tasks in Progress: | Each member works on the presentation slide. Jerry: introduction, background, technology part. Brian: testing, debugging. Julian: project plan, methodology. Peter and Sam: Product part, design pattern, game flow.
| Next Tasks: | Finish the presentation slides. Modification of contents: Project Plan Abstract/by Peter; Design Constraints/by Julian; Puzzle UI class diagram/by Sam Preparing program execution demo/by Peter.
Week 13-1 (week 47, 2022) | Objectives: | Prepare for the presentation slide, and start some rehearsal about the presentation | All members | Jerry
| Completed Tasks: | Rehearsal about the presentation with time measures & run-down management. Modification of slide flow and content/by Jerry and Brian. Modification of Puzzle UI class diagram/by Sam.
| Tasks in Progress: | Modify some slides and presentation flow. Modification of contents: Project Plan Abstract/by Peter; Design Contraints/by Julian.
| Next Tasks: | Continue to rehearse the presentation to ensure all things go right & within the 20min time limit.
Week 13-2 (week 47, 2022) | Objectives: | Presentation rehearsal. | All members | Jerry
| Completed Tasks: | Rehearsal
| Tasks in Progress: | Modification of contents: Project Plan Abstract/by Peter; Design Contraints/by Julian. Modify contents of Project schedule, tracking & control section/by Julian.
| Next Tasks: | Close the project: Finalize all documentation, and program packaging and submit to Canvas.
Week 14 (week 48, 2022) | Objectives: | Project closing | All members | Jerry
| Completed Tasks: | Complete rewrite of the contents of Project Plan Abstract/by Peter; Design Constraints/by Julian. Completed rewrite of the contents of the Project schedule, tracking & control section/by Julian. Project closing/by Peter
| Tasks in Progress: | Nil
| Next Tasks: | Nil